PROJECT REPORT

Cloud-Native Construction Project Intelligence Platform

for Predictive Delay and Cost Monitoring

Using Power BI, Docker and Kubernetes

Literature Review, Research Gap, Objectives, and Proposed Architecture

Domain: Civil Engineering / Construction Project Controls

Core Technologies: Microsoft Power BI | Docker | Kubernetes | Python | PostgreSQL

Prepared as a project concept and literature-based design report

# 1. Abstract

Civil engineering and construction projects continuously generate schedule, cost, progress, resource, and site-status data, yet these data are frequently fragmented across spreadsheets and project-control applications. Existing research demonstrates the value of visual analytics, Power BI dashboards, BIM-based progress monitoring, and data-driven delay management; however, the reviewed studies generally treat visualization, prediction, data integration, and system deployment as separate concerns. This project proposes a cloud-native Construction Project Intelligence Platform that integrates near-real-time project-control data, computes cost and schedule performance indicators, estimates delay risk, and presents decision-ready information through Microsoft Power BI. The backend is packaged as Docker containers and orchestrated by Kubernetes to provide repeatable deployment, service isolation, health monitoring, recovery, and horizontal scaling. A centralized PostgreSQL database stores project-control and analytics results, while containerized ingestion and analytics services perform validation, KPI computation, and optional machine-learning-based delay-risk scoring. Power BI consumes curated data from the platform to visualize cost variance, schedule variance, CPI, SPI, progress trends, and high-risk activities. The proposed work addresses a gap identified across six reviewed studies: the absence of a single, reproducible, scalable implementation that combines integrated construction data, predictive project-control analytics, Power BI visualization, and cloud-native orchestration.

Keywords: Power BI, Docker, Kubernetes, construction project controls, delay risk, cost overrun, data-driven decision-making, visual analytics.

# 2. Literature Review

Construction project management is increasingly moving from static reporting toward interactive visual analytics and data-driven decision support. Chiu and Russell [1] established an early design foundation by proposing a top-down construction-management data visualization environment. Their work emphasized analytical reasoning for time management, including baseline schedule assessment, planned-versus-actual comparison, and diagnosis of deviations. The study showed that visualization can reduce the cognitive burden created by large and heterogeneous project datasets, but its detailed case emphasis was primarily on schedule/time management rather than an integrated cost, risk, and deployment platform.

A decade later, Al-Sulaiti et al. [2] demonstrated a more dashboard-oriented approach for Engineering, Procurement, and Construction (EPC) performance assessment. Their workflow organized project data using an Entity Relationship Diagram, retrieved the database into Microsoft Power BI, and used KPIs and interactive visualizations to support progress reporting and performance monitoring. This work provides direct evidence for Power BI as a practical project-control visualization layer; however, it focuses mainly on assessment and reporting rather than a predictive and cloud-native backend architecture.

Radman et al. [3] widened the scope from dashboards to a full data lifecycle for construction delay management. Through a systematic literature review, they classified digital technologies for data collection, screening/analysis, and presentation, and proposed a process-based framework centered on a cloud-based relational database. Their framework explicitly includes sensors, IoT, BIM, planning tools, Primavera, and BI tools such as Power BI. Importantly, the authors state that integrated management systems, relationships among entities, data-flow types, and big-data centralization require further investigation. This is highly relevant to the proposed project because it motivates an implementable integration layer rather than a conceptual data-flow framework alone.

Gajera [4] specifically examined the integration of Power BI with project-control systems for near-real-time construction cost tracking. The paper synthesizes secondary sources and industry cases and reports improvements in visibility, reporting, stakeholder communication, and timely decision-making. At the same time, it identifies data compatibility, cleansing, user adoption, and training as recurring implementation challenges. The study also acknowledges that it relies on secondary data and lacks primary experimental evidence, leaving room for an implemented prototype whose data integration and deployment behavior can be directly evaluated.

Zhang and Wang [5] move beyond descriptive dashboards by quantifying schedule-delay risk. They combine BIM, historical duration data, probabilistic critical-path analysis, and a second-order reliability method (SORM) to identify critical tasks and estimate the probability of schedule failure. A real construction case with a 27-activity schedule is used for validation. The work demonstrates the value of proactive, data-driven risk estimation, but the authors identify significant setup effort, BIM modeling constraints, limited suitability for linear projects, and continued dependence on manual progress reporting. This suggests a need for a more general data pipeline in which predictive or risk-scoring services can consume standardized project-control records independently of one BIM-specific workflow.

Sanusi [6] presents the broad managerial argument for data-driven decision-making (DDDM) in civil engineering, linking predictive analytics, BIM, IoT, machine learning, and real-time surveillance to reduction of project delays and cost overruns. The paper also summarizes practical barriers: poor data quality, integration difficulties, organizational resistance, skill gaps, and upfront investment. Taken together, the six studies reveal an evolution from visualization, to BI dashboards, to integrated data lifecycles, and finally to predictive decision support. What remains underdeveloped across the reviewed set is a reproducible deployment architecture that integrates these ideas into one scalable system using modern containerization and orchestration.

# 3. Related Work

Table 1. Comparative analysis of six studies used to derive the proposed project.

| Study | Purpose | Problem Definition | Solution / Method | Key Observation | Limitation |
| --- | --- | --- | --- | --- | --- |
| Chiu & Russell (2011) [1] | Design a construction-management visual analytics environment using a top-down approach, with emphasis on time management. | Large and heterogeneous construction datasets make it difficult for managers to understand schedule status, dependencies, and causes of deviation in a timely manner. | Defines analytical-reasoning requirements and implements interactive visualizations for baseline schedule quality, planned-vs-actual performance, and deviation analysis; demonstrates the environment on actual project data. | Interactive visualization can support planning, monitoring, diagnosis, and cause-effect reasoning more effectively than static reporting. | Case emphasis is mainly time/schedule management; broader CM functions require extension. Validation is case-based and does not address predictive analytics or cloud-native deployment. |
| Al-Sulaiti et al. (2021) [2] | Use data analytics and a Power BI dashboard to assess EPC project performance and improve reporting/monitoring. | EPC data are distributed and difficult to interpret through conventional reports, reducing visibility of project performance. | Creates an ERD for collected project data, retrieves the database into Microsoft Power BI, and visualizes project KPIs for performance assessment. | Power BI-based analytics can make performance information easier to access and can support portfolio, contractor, progress, and managerial monitoring. | Demonstrated through a real-company case with limited generalizability; primarily descriptive KPI monitoring, with limited predictive/early-warning capability. |
| Radman et al. (2022) [3] | Investigate digital technologies for delay management and propose a data-lifecycle framework for real-time construction information. | Construction technologies generate high-volume data, but data collection, analysis, presentation, and decision-making are fragmented and insufficiently integrated. | Systematic literature review plus thematic analysis; proposes a three-layer process framework covering data collection, database/analysis, and decision-making using IoT, BIM, scheduling tools, DBMS, and BI tools including Power BI. | Centralized data flow and timely reports can help decision-makers detect delay-related problems earlier; a cloud-based relational DBMS can act as the integration engine. | Framework is mainly conceptual; authors call for more investigation of integrated management systems, entity relationships, data-flow types, analysis efficiency, and big-data centralization. |
| Gajera (2023) [4] | Examine how integrating Power BI with project-control systems can improve near-real-time cost tracking and visualization. | Traditional cost reporting is slow and fragmented, while combining heterogeneous project-control data creates compatibility and adoption challenges. | Qualitative secondary-data synthesis of literature, industry reports, and case studies on Power BI integration, cost visibility, decision-making, and stakeholder engagement. | Reports indicate improved cost visibility, faster reporting, and more timely decisions when Power BI is integrated with project-control data. | No primary implementation or controlled experiment; findings depend on secondary sources. Data compatibility, cleansing, training, and resistance to change remain key issues. |
| Zhang & Wang (2023) [5] | Quantify construction schedule-delay risk using data-driven BIM and probabilistic reliability analysis. | Manual progress management is time-consuming and error-prone, while uncertain task durations make it difficult to identify critical schedule-failure risk proactively. | Combines BIM, historical duration estimation, probabilistic critical-path modeling, SORM, visualization, and a real 27-activity construction case. | The method can dynamically estimate schedule-failure risk and identify critical tasks with a balance of computational efficiency and accuracy. | Complex initial quota-database setup; some work is difficult to model in BIM; limited suitability for linear projects; manual progress reports are still required and can introduce errors. |
| Sanusi (2024) [6] | Explain how data-driven decision-making can reduce delays and cost overruns in civil engineering projects. | Traditional management methods struggle with complex, multidimensional projects and often react too late to schedule and cost problems. | Synthesizes applications of predictive analytics, BIM, IoT, machine learning, historical data, and real-time monitoring for forecasting, resource allocation, and coordination. | DDDM can improve forecasting, risk detection, resource allocation, accountability, and cost optimization when reliable data and organizational support are available. | Data quality, system integration, organizational culture, skills, cybersecurity/infrastructure, and upfront investment can constrain adoption; evidence is largely review/case-based rather than one validated end-to-end system. |

# 4. Research Gap Identified

The reviewed literature establishes four important capabilities: (i) interactive construction data visualization [1], (ii) Power BI-based performance dashboards [2,4], (iii) integrated real-time data lifecycles and centralized databases [3], and (iv) proactive delay-risk or predictive decision support [5,6]. However, these capabilities are mostly studied independently rather than implemented as one deployable platform.

Across the six reviewed studies, no work presents a single reproducible architecture in which heterogeneous project-control data are ingested by containerized services, validated and stored centrally, processed for cost/schedule KPIs and predictive delay-risk indicators, orchestrated by Kubernetes for fault recovery and scaling, and exposed to Power BI as the management visualization layer. Radman et al. [3] explicitly call for further investigation into integrated management systems, data relationships, data-flow types, and big-data centralization, while Gajera [4] highlights compatibility and implementation problems. Zhang and Wang [5] demonstrate quantitative risk analysis but retain setup and manual-reporting constraints. These combined limitations motivate a cloud-native integration and deployment contribution.

Research gap statement: There is a need for a scalable, reproducible, cloud-native construction project intelligence platform that unifies data integration, performance analytics, predictive delay-risk monitoring, and Power BI visualization while explicitly addressing deployment reliability and scalability through Docker and Kubernetes.

# 5. Objectives

Design a unified data model for construction project-control information, including project, activity, planned and actual dates, planned and actual cost, earned value, progress percentage, resources, and risk indicators.

Develop a containerized data-ingestion and validation service that accepts CSV/Excel exports or REST-based project updates and stores standardized records in PostgreSQL.

Implement an analytics service to calculate Earned Value Management and schedule indicators such as Cost Variance (CV), Schedule Variance (SV), Cost Performance Index (CPI), Schedule Performance Index (SPI), and progress deviation.

Implement a lightweight delay-risk module using historical/simulated project data to classify or score activities/projects according to the probability of delay, with the model kept modular so alternative algorithms can be compared.

Create Power BI dashboards for portfolio overview, project drill-down, cost performance, schedule performance, delay-risk alerts, and trend analysis.

Package backend services with Docker and deploy them on Kubernetes using Deployments, Services, ConfigMaps/Secrets, health checks, persistent storage, and optional Horizontal Pod Autoscaling.

Evaluate the platform for analytical correctness, dashboard usefulness, deployment repeatability, recovery from service failure, and response-time/scaling behavior under increasing data or request loads.

# 6. Proposed Design and Architecture

## 6.1 Design Overview

The proposed system separates project data collection, analytics, storage, orchestration, and visualization into modular components. Power BI is used as the user-facing business-intelligence layer, while Docker and Kubernetes operate the backend platform. Power BI itself is not containerized; instead, it connects to curated database views or an API exposed by the Kubernetes-hosted services. This design makes the mandatory technologies functionally meaningful rather than merely included as independent tools.

High-level data flow: Project Data -> Ingestion API -> PostgreSQL -> Analytics + Delay-Risk Service -> Curated Views/API -> Power BI

Docker packages the backend services; Kubernetes deploys and manages them; PostgreSQL stores standardized data; Power BI consumes curated outputs.

## 6.2 Major Components

| Layer / Component | Technology | Role in the Proposed System |
| --- | --- | --- |
| Data Sources | CSV/Excel exports, REST updates, optional schedule/BIM-derived data | Provide planned/actual dates, cost, progress, resource, and site-status information. |
| Ingestion Service | Python + FastAPI, Docker | Receives project updates, validates schema, rejects invalid records, and writes standardized data to the database. |
| Central Data Store | PostgreSQL + Persistent Volume | Stores projects, activities, cost/progress histories, computed KPIs, risk scores, and audit timestamps. |
| Analytics Service | Python, Pandas/NumPy, Docker | Computes CV, SV, CPI, SPI, completion variance, rolling trends, and project-level summaries. |
| Delay-Risk Service | Scikit-learn or probabilistic scoring, Docker | Produces a delay-risk probability/score and exposes factors used by the dashboard. |
| Orchestration Layer | Kubernetes | Manages service discovery, replicas, health checks, restarts, configuration, secrets, storage, and optional autoscaling. |
| Visualization Layer | Microsoft Power BI | Displays executive KPIs, schedule/cost trends, high-risk activities, project drill-down, and alerts. |

## 6.3 Logical Architecture

1) Project-control files or API updates enter the Ingestion Service. 2) The service validates field types, dates, identifiers, and missing values before storing data in PostgreSQL. 3) The Analytics Service periodically or event-wise reads new records and computes EVM/schedule KPIs. 4) The Delay-Risk Service uses features such as progress deviation, SPI, cost trend, historical activity duration, and resource variance to generate a risk score. 5) Curated database views expose only reporting-ready fields. 6) Power BI reads these views and refreshes management dashboards. 7) Kubernetes continuously supervises the backend pods and restarts unhealthy services; if request volume increases, the ingestion/analytics replicas can be scaled without redesigning the application.

| Kubernetes Object | Applies To | Purpose |
| --- | --- | --- |
| Deployment | Ingestion, analytics, risk services | Defines replicas and enables rolling updates/restarts. |
| Service | API and database access | Provides stable internal/external networking endpoints. |
| ConfigMap | Non-sensitive settings | Stores refresh intervals, feature flags, and environment configuration. |
| Secret | Database credentials/API secrets | Separates credentials from container images and source code. |
| PersistentVolumeClaim | PostgreSQL | Preserves project data across pod restarts. |
| Liveness/Readiness Probes | Backend services | Detects failed instances and prevents traffic from reaching unhealthy pods. |

## 6.4 Power BI Dashboard Design

Executive Overview: total budget, actual cost, earned value, overall completion, CPI, SPI, number of high-risk activities, and projects requiring attention.

Cost Performance: budget vs. actual/earned value, cost variance trend, top cost-overrun activities, and project/contractor filters.

Schedule Performance: planned vs. actual progress, schedule variance, SPI trend, delayed activities, critical/high-risk activity list, and milestone status.

Delay-Risk View: risk probability/score, risk category, main contributing features, and time trend for early-warning monitoring.

Operational Health (project demonstration): timestamp of last update, number of processed records, and backend service status/refresh information where available.

## 6.5 Proposed Data Model

A relational design keeps the Power BI model simple while retaining historical records. The minimum entities are Project, Activity, ProgressUpdate, CostRecord, ResourceRecord, KPIResult, and RiskResult. Project and Activity hold stable master data; ProgressUpdate and CostRecord are append-only time-series facts; KPIResult and RiskResult store computed outputs with timestamps. This structure directly addresses the data-centralization and compatibility problems emphasized in the literature [3,4,6].

| Entity | Example Fields | Purpose |
| --- | --- | --- |
| Project | project_id, name, baseline_start, baseline_finish, budget | Project-level master record. |
| Activity | activity_id, project_id, planned_start/finish, planned_cost | Schedule work package / task. |
| ProgressUpdate | activity_id, timestamp, actual_progress, actual_start/finish | Historical site/progress updates. |
| CostRecord | activity_id, timestamp, actual_cost, earned_value | Cost and earned-value facts. |
| KPIResult | timestamp, CV, SV, CPI, SPI, progress_variance | Reporting-ready project-control indicators. |
| RiskResult | timestamp, risk_score, risk_class, top_factors | Predictive/early-warning output for Power BI. |

## 6.6 Evaluation Plan

The project should be evaluated not only as a dashboard but also as a deployable system. This provides a measurable contribution aligned with the identified gap.

| Evaluation Area | Example Measure | Expected Evidence |
| --- | --- | --- |
| Analytical correctness | Verify CV, SV, CPI, SPI and progress variance against hand-calculated test cases. | Unit-test results and comparison table. |
| Delay-risk model | Use accuracy/F1/AUC for classification, or MAE/RMSE if predicting delay days. | Train/test evaluation on public or carefully simulated data. |
| Data pipeline | Invalid rows rejected; valid rows appear in database and dashboard within defined refresh interval. | Integration tests and timestamp logs. |
| Kubernetes resilience | Delete an API pod and observe recovery; verify that the Service remains available. | Pod restart/recovery screenshots or logs. |
| Scalability | Compare API response time or throughput with one vs. multiple replicas. | Small load-test table/graph. |
| Power BI usefulness | Check whether users can identify over-budget, behind-schedule, and high-risk items using drill-down views. | Scenario-based dashboard demonstration or small user feedback study. |

# 7. References

[1] C.-Y. Chiu and A. D. Russell, “Design of a construction management data visualization environment: A top-down approach,” Automation in Construction, vol. 20, no. 4, pp. 399–417, 2011. DOI: 10.1016/j.autcon.2010.11.010. Source

[2] A. Al-Sulaiti, M. Mansour, H. Al-Yafei, S. Aseel, M. Kucukvar, and N. C. Onat, “Using Data Analytics and Visualization Dashboard for Engineering, Procurement, and Construction Project’s Performance Assessment,” 2021 IEEE 8th International Conference on Industrial Engineering and Applications (ICIEA), pp. 207–211, 2021. DOI: 10.1109/ICIEA52957.2021.9436728. Source

[3] K. Radman, M. B. Jelodar, R. Lovreglio, E. Ghazizadeh, and S. Wilkinson, “Digital technologies and data-driven delay management process for construction projects,” Frontiers in Built Environment, vol. 8, 1029586, 2022. DOI: 10.3389/fbuil.2022.1029586. Source

[4] R. Gajera, “Integrating Power BI with Project Control Systems: Enhancing Real-Time Cost Tracking and Visualization in Construction,” International Journal of Scientific Research in Civil Engineering, vol. 7, no. 5, pp. 154–160, 2023. DOI: 10.32628/IJSRCE123761. Source

[5] S. Zhang and X. Wang, “Quantifying Schedule Delay Risk in Construction Projects: A Data-Driven Approach with BIM and Probabilistic Reliability Analysis,” Advances in Civil Engineering, vol. 2023, Article ID 5525655, 2023. DOI: 10.1155/2023/5525655. Source

[6] B. O. Sanusi, “The Role of Data-Driven Decision-Making in Reducing Project Delays and Cost Overruns in Civil Engineering Projects,” SAMRIDDHI: A Journal of Physical Sciences, Engineering and Technology, vol. 16, no. 4, pp. 182–192, 2024. DOI: 10.18090/samriddhi.v16i04.08. Source